## STP
Software Test Plan
1. Software Test Plan
version: | 1
Created: | 2023-02-28
Name of product: | Less App
Prepared by: | Raanan
2. Indroduction
The purpose of the STP document is to define a framework plan for testing. This framework program will include all subjects
Relevant to the planning and execution of the tests
3. Objectives
3.1. This test plan describes the testing approach, the objectives, scope, schedule, risks, approach, Enter&Exit criteria, Test Tree and Testing methodology.and overall framework that will drive the testing.
3.2. The work method planned for the tests:
o Strategy and topics for review
o The objectives of the tests
o The testing process
o The work method
o The testing environment
o Planned timetable
4. Tree Testing
4.1. Sign Up:
4.1.2 User details
4.1.3 Details confirmation
4.2 Sign In:
4.2.1 Mail
4.2.2 Password
4.3 Guest:
4.3.1 Read option to signup
4.3.2 Confirm contract form
5. Entry and exit criteria
5.1 Android mobile device
5.2 Exit criteria
5.2.1 0 Critical bugs
5.2.2 0 Regression bugs
5.2.3 Maximum 3 Medium bugs
5.2.4 Maximum 3 Low bugs
6. Test strategy
6.1 Test Approach
The purpose of the test is to check and do validation on the part of the client and server.
The tests will be performed when a customer enters the system and every action by the customer must be checked and whether everything is working properly
The tests will be excucte every day and loads tests a once a week
6.2 Test automation
An automation team will be responsible for creating automated tests that will be tested according to test cases, and will create load tests
7. The types of tests that will be tested
7.1 Sanity Testing
Sanity checks will be performed in order to quickly check whether after fixing bugs everything works as it should - fixing bugs did not cause new bugs.
7.2 Smoke Testing
Small tests are done before running a set of functional tests, which saves time and money.
7.3 User interface (GUI) tests
Checking the elements that appear on the screen for a customer, the customer's actions are being performed correctly.
7.4 Functional tests
Testing all client proccesses
The processes should be correct from end to end
7.5 Intergration testing
Compatibility tests of app
7.6 Data integrity checks
Check that all the data save and correct
Test the data after kinds of tests
7.7 Regresstion testing
Repeated tests on a previously tested module, after adjustments and/or changes in various parts
in the system, in order to discover faults that entered the system as a result of those changes
7.8 Permission tests
Test of permmision by client type
This is for create security for clients and pevents failurs of login
8. Testing methology
Validation and failure management
Failures which will be found during the testing will be categorized |  |  | :
Critical: | Bug causes to crash system
High: | Bug causes to lack of program functually
Medium: | Causing the disruption of the test
Low | minimum impact like error messages
9. Bug status
New: | Just opened
Open: | Opened bug which not solved
Rejected: | Bug which rejected -not a bug
Fixed: | Solved bug
Closed: | Bug which closed because solved/rejected
Reopen: | Bug open again because the bug is reproducing
10. Assumptions / Risks
10.1 Assumptions
All the conditions that need to be met for us to continue successfully.
Tests should complete successfully with no failures.
10.2 Risks
Risks must be avoided in order not to damage critical things.
For example changing functions, tests, and new things you want to add
11. Test enviroment
11.1 Computer with 8 GB RAM, Windows 10 and Chrome
11.2 Android mobile phone
12. ROLES & RESPONSIBILITIES
12.1 QA Testers
Develop test cases
Report Bugs
Regression Testing
12.2 QA Automation team
Develop tests
Loads tests
Version sanity
12.3 Test lead
Prepare STP
Preparing Test Summary Report
Evaluating exit criteria

## Bugs
bugs
Bug 1
Title
Want to proceed as a guest' button doesn't work
Device
Mobile(Galaxy S 10)
Steps
1. Open app
2. Confirm start screen
3. Click 'I want proceed as a guest'
Exception
Click on 'Want to proceed as a guest button' should to guest screen
Actual
Nothing happens
Bug 2
Title
Screen stuck on login when sign me button clicked
Device
Mobile(Galaxy S 10)
Steps
1. Open app
2. Confirm start screen
3. Click on mail icon for register by mail
4. Fill all the fileds
5. Click register
Exception
Except to get success regitration
Actual
Stuck on login
Bug 3
Title
English text wrriten on right side
Device
Mobile(Galaxy S 10)
Steps
1. Open app
2. Confirm start screen
3. Click I have account
4. Insert mail
Exception
English text should be wrriten on left side
Actual
The text is on right side
Bug 4
Title
Facebook button doesn't work in mobile
Device
Mobile(Galaxy S 10)
Steps
1. Open app
2. Confirm start screen
3. Click on facebook icone
Exception
Screen moves to facebook page
Actual
Nothing happens
Bug 5
Title
Screen stuck on login when enter to my account button clicked
Device
Mobile(Galaxy S 10)
Steps
1. Open app
2. Confirm start screen
3. Click on I have account
4. Fill the fileds
5. Click ok
Exception
Screen moves to account user
Actual
Nothing happens